## Product Roadmap
Agile Product Roadmap
<Agile Development Project> | Q2 |  |  | Q3 |  |  | Q4
| April | May | June | July | August | September | October | November | December
Group 1
Group 2
Group 3
Group 4
Group 5
Create an Agile Product Roadmap in Smartsheet
Manufacturing (Product 1)
Online retailer
Manufacturing (Product 2)
Logistics
Logistics

## Project Charter
Agile Project Charter
General Project Information
Project Name | Agile Development for Manufacturing
Project Champion | Scope,CityU
Project Sponsor | Bryan Cheung Wai Chung
Project Manager | Ivan Cheung Yan Hin
Stakeholders | Beeno Fung, Desmond Chu, Martin Kwong, Daniel Tung
Expected Start Date | 2018-01-04
Expected Completion Date | 2018-03-14
Project Details
Mission | 1. Contact with customers 2. Producing product 3. transport the product to the customers 4. Communicate with customer
Vision | 1. Manufacture leader in Hong Kong 2. Top 10 manufacture company in the world
Scope | 1.Login system for customers 2. Receive order from online retailer and check inventory 3.Deliver the products to customer through logistics provider
Success Metrics | Customers like our product, Customers loyalty, produce produce within budgets and scheduled time
Date: 14-03-2018 | Signature: Bryan.C
Create an Agile Project Charter in Smartsheet

## Project Plan
Agile Project Plan
Project Name | Agile Development for Manufacturing
Project Manager | Ivan Cheung Yan Hin
Project Deliverable
Scope Statement
Start Date | 2018-01-04
End Date | 2018-03-14
Overall Progress | 99%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Ivan Cheung | 2018-01-24 | 2018-02-07 | 14 | Complete
Service Blueprint | Beeno Fung | 2018-01-24 | 2018-02-05 | 12 | Complete
Get user requirement | Dainel Tung | 2018-01-24 | 2018-02-05 | 12 | Complete
Database Design | Martin Kwong | 2018-01-24 | 2018-02-07 | 14 | Complete
Sprint 2 | Beeno Fung | 2018-02-07 | 2018-02-21 | 14 | Complete
System Design | Martin Kwong | 2018-02-07 | 2018-02-20 | 13 | Complete
Database implementation | Ivan Cheung | 2018-02-07 | 2018-02-19 | 12 | Complete
Program development | Dainel Tung | 2018-02-07 | 2018-02-21 | 14 | Complete
Sprint 3 | Dainel Tung | 2018-02-21 | 2018-03-07 | 14 | Complete
Testing | Martin Kwong | 2018-02-21 | 2018-03-05 | 12 | Complete
Debugging | Beeno Fung | 2018-02-21 | 2018-03-06 | 13 | Complete
Documentation | Ivan Cheung | 2018-02-21 | 2018-03-07 | 14 | Complete
Create an Agile Project Plan in Smartsheet

## User Story
Agile User Story Template
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | Owner | Check file | Receive order
2 | Owner | Enter order | Receive payment
3 | Customer | Contact manufacturer | Send order
4 | Employee | Check inventory | Prepare the order
5 | Employee | Calculate the cost | Generate the bill statement
6 | Employee | Contact logistic provider | Delivery the product
7 | Employee | Receive the order | Process the order
8 | Employee | Check inventory status | Calculate the amount of the cost
9 | Employee | Calculate the order quantity | Update inventory
10 | Employee | Deliver the report | Inform customers
Track Agile User Stories in Smartsheet

## Product Backlog
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | No | No | High | Complete | 30 | No
spreadsheet | Yes | Yes | High | Complete | 8 | Yes
Web page | Yes | Yes | Medium | Complete | 10 | Yes
Building Inventory | Yes | Yes | High | Complete | 12 | Yes
Sprint 2 | Yes | Yes | Medium | Complete | 180 | Yes
Building the product list | Yes | Yes | Low | Complete | 48 | Yes
Database | Yes | Yes | High | Complete | 56 | Yes
Program | No | No | Medium | Complete | 76 | Yes
Sprint 3 | Yes | No | Medium | In Progress | 180 | No
Show inventory status | Yes | No | Medium | Complete | 60 | Yes
Receive order | No | Yes | High | Complete | 55 | Yes
Update inventory | Yes | No | High | Complete | 65 | Yes
Create a Product Backlog in Smartsheet

## Sprint Backlog
Sprint Backlog Template ( Remaining outstanding efforts in hours )
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 | 28
Smartsheet | 4 | Prepare a excel template | Complete | 5 | 4 | 3 | 2 | 2 | 1 | 0
Service Blueprint | 8 | Design project flow | Complete | 3 | 2 | 2 | 1 | 0 | 0 | 0
Database Design | 16 | Design database by MySQL | Complete | 9 | 7 | 6 | 4 | 3 | 2 | 2
Project Plan | 4 | Plan project schedule | Complete | 4 | 3 | 2 | 1 | 1 | 1 | 0
User Story #2 | 40
System Design | 12 | Design website functions | Complete | 7 | 6 | 5 | 4 | 4 | 2 | 0
Database implementation | 12 | Set up databse & input data | Complete | 8 | 7 | 5 | 3 | 2 | 2 | 0
Website development | 16 | Develop website by open source | Complete | 14 | 12 | 10 | 8 | 6 | 4 | 2
User Story #3 | 28
Testing | 8 | Write testing plan | Complete | 4 | 3 | 3 | 2 | 2 | 1 | 0
Debugging | 12 | Debug web program | Complete | 7 | 6 | 4 | 2 | 1 | 1 | 0
Documentation | 8 | Write agile documents | Complete | 7 | 6 | 5 | 4 | 3 | 2 | 0
User Story #4 | 8
Task
Task
Task
Task
User Story #5 | 3
Task
Task
Task
Task
Total |  |  |  | 68 | 56 | 45 | 31 | 24 | 16 | 4
S

## Test Plan
Agile Test Plan
Project Name | Agile Development for Manufacturing |  | Browser: | Google Chrome, Microsoft Internet Explorer
Test Case ID | 1 |  | Version: | 1
Written By: | Dainel Tung |  | Description: | Check whether the testing results are the same as expected or not
Tested By: | Ivan Cheung |  | Tested On: | Mircosoft Window 10
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2018-02-21 | Logging in | Go to the home page | Go to the home page | Yes
2 | 2018-02-28 | Create a order form | A new order will be added and displayed | A new order is added and displayed | Yes
3 | 2018-03-03 | Update a order info such as status/quality | The order info will be changed | The order info change correctly | Yes
4 | 2018-03-07 | Check inventory status | A list of inventory info will be displayed | A list of inventory info is displayed | Yes
Create a Test Plan in Smartsheet

## Release Plan
Agile Release Plan
Sprint | Task | Start | End | Duration | Status | Release Date | Goal
1 | Service Blueprint | 2018-01-24 | 2018-02-07 | 14 | Released | 2018-02-07
1 | Get user requirement | 2018-01-24 | 2018-02-07 | 14 | Released | 2018-02-07
1 | Database Design | 2018-01-24 | 2018-02-07 | 14 | Released | 2018-02-07
2 | System Design | 2018-02-07 | 2018-02-21 | 14 | Released | 2018-02-21
2 | Database implementation | 2018-02-07 | 2018-02-21 | 14 | Released | 2018-02-21
2 | Program development | 2018-02-07 | 2018-02-21 | 14 | Released | 2018-02-21
3 | Testing | 2018-02-21 | 2018-03-07 | 14 | Released | 2018-03-07
3 | Debugging | 2018-02-21 | 2018-03-07 | 14 | Released | 2018-03-07
3 | Documentation | 2018-02-21 | 2018-03-15 | 22 | Ongoing | 2018-03-15
0
Create an Agile Release Plan in Smartsheet